## Sheet1
Phases and Tasks | Jan | Feb | Mar | April | May | Jun | Jul | Aug | Sep | Oct
Phase 1
Kickoff meeting at Town Hall | bar: Jan
Overview, History | bar: Jan
Environmental (external & internal) Scans | bar: Jan
Labor market analysis | bar: Jan
Forecast future growth | bar: Feb
Steering Committee Feedback Throughout | bar: Jan to April
Phase 2
Division/area questionnaire | bar: Feb
Division/area interviews | bar: Mar
Phase 3
Institutional effectiveness | bar: Feb
Goal setting with Steering Committee | bar: Mar to April
Refine draft | bar: April to May
Phase 4
Post revised plan to web | bar: Aug
Presentation at college opening day | bar: Aug
Phase 5
Finalize campus inputs | bar: Sep
Final presentation to Board | bar: Oct
*spring 2023 ends April 29th (Saturday)
** first day of fall 2023 classes is likely going to be August 28th (Monday)